## Summary
SignalLanes Feature/User-Story Status
Workbook purpose | Canonical SignalLanes feature/user-story status ledger | Status | Count
Generated | 2026-06-27 | Passed | 26
Repo | /Users/sliven/Documents/My Github/SignalLanes | Fixed + retested | 3
Stories inventoried | 41 | Inspection/build verified | 12
Test/check rows | 13 | Open errors | 0
Defects fixed or preserved | 3 | Total stories | 41
Open errors after retest | 0
Main validation | swift run SignalLanesCoreSmokeTests; swift build; CLI queue/status/language; build-app; package-release
UI automation caveat | AppKit menu/floating click and drag behaviors are code/build inspected because no UI automation harness exists; an app process was already running and was not relaunched or killed.

## Feature Stories
ID | Area | User story | Expected behavior from code | Source files | Validation | Status | Errors found | Post-fix result | Notes
F001 | App startup | As a macOS user, I can launch SignalLanes as a menu bar utility without a Dock icon. | AppDelegate sets accessory activation, configures the NSStatusItem, shows the floating light when enabled, runs an immediate refresh, and schedules 5-second refreshes. | Sources/SignalLanes/main.swift; Scripts/build-app.sh | T002, T008, T009, T012 | Passed | None | No fix needed | Runtime process already existed, so no relaunch/kill was performed.
F002 | Status priority | As a user, I see the most attention-worthy status first. | LightState ordering makes idle < working < waitingForPermission, so yellow overrides red and green, and red overrides green. | Sources/SignalLanesCore/LightState.swift; Sources/SignalLanesCore/AgentDetector.swift | T001, T004 | Passed | None | No fix needed
F003 | Menu status | As a menu bar user, I can open the menu and see overall status, scan time, waiting, running, and stopped sections. | makeMenu adds summary, last scan, three queue sections, and common commands; empty sections show localized None. | Sources/SignalLanes/main.swift | T002, T004, T005, T006 | Passed | None | No fix needed | Menu click itself is AppKit-inspected, not automated.
F004 | Menu task details | As a user, I can inspect task details from the menu when a queue item exists. | Each group menu item includes reason, project path, session ID or grouped session list, source, and up to five process summaries/tooltips. | Sources/SignalLanes/main.swift | T004, T006 | Passed | None | No fix needed
F005 | Refresh command | As a user, I can request a fresh detection scan from the menu. | Refresh Now calls refreshFromMenu, which triggers the same guarded async refresh path as the timer. | Sources/SignalLanes/main.swift | T002, code inspection | Verified by inspection/build | None | No fix needed | No AppKit menu automation harness exists in repo.
F006 | Detection failure UX | As a user, if detection fails I see an explicit failure state rather than stale status. | updateStatusItem(errorMessage:) sets yellow image, tooltip error, floating failure message, disabled menu error row, and common commands. | Sources/SignalLanes/main.swift | T002, code inspection | Verified by inspection/build | None | No fix needed
F007 | Floating light visibility | As a user, I can hide/show the floating light and the choice persists. | FloatingSignalLanesWindowController stores floatingLight.isEnabled in UserDefaults and orderFront/orderOuts the panel. | Sources/SignalLanes/FloatingSignalLanesWindowController.swift; Sources/SignalLanes/main.swift | T002, T008, code inspection | Verified by inspection/build | None | No fix needed | Runtime click not automated.
F008 | Floating position | As a user, I can drag the floating light and reset its position. | Mouse drag moves the panel, windowDidMove saves origin, reset removes saved origin and constrains to visible frame. | Sources/SignalLanes/FloatingSignalLanesWindowController.swift; Sources/SignalLanes/main.swift | T002, T008, code inspection | Verified by inspection/build | None | No fix needed | Runtime drag not automated.
F009 | Floating filters | As a user, I can click Running, Waiting, or Stopped segments to filter the task list. | mouseDown/mouseUp detect status segment rects and set selectedFilterState, reset scroll, redraw, and update cursors. | Sources/SignalLanes/FloatingSignalLanesWindowController.swift | T002, code inspection | Verified by inspection/build | None | No fix needed | Runtime click not automated.
F010 | Floating scroll | As a user with many tasks, I can scroll the floating list. | scrollWheel clamps scrollOffset between zero and groups.count - maxVisibleTasks; medium shows 8, large shows 11, small shows 1. | Sources/SignalLanes/FloatingSignalLanesWindowController.swift | T004, T002, code inspection | Verified by inspection/build | None | No fix needed | Live queue had enough rows to exercise data shape; UI scroll not automated.
F011 | Floating row activation | As a user, I can click a task row to switch to the matching IDE or app. | Rows map to task groups; click without drag calls activateApplication(for:) using process/project identity and optional Accessibility precision. | Sources/SignalLanes/FloatingSignalLanesWindowController.swift | T002, code inspection | Verified by inspection/build | None | No fix needed | Activation side effects were not executed automatically.
F012 | Themes | As a user, I can switch the floating light theme. | Theme menu offers Midnight Glass, Calendar Light, and Weather Blue; selection is stored and redraws/resizes the panel. | Sources/SignalLanes/FloatingSignalLanesWindowController.swift; Sources/SignalLanes/main.swift | T002, T008, code inspection | Verified by inspection/build | None | No fix needed
F013 | Display size | As a user, I can choose small, medium, or large floating display sizes. | Display size menu stores the selected case; preferred size, row height, visible task count, fonts, and labels adjust. | Sources/SignalLanes/FloatingSignalLanesWindowController.swift; Sources/SignalLanes/main.swift | T002, T008, code inspection | Verified by inspection/build | None | No fix needed
F014 | Language switching | As a user, I can switch English, Traditional Chinese, or Simplified Chinese UI language. | Language menu persists AppLanguage, updates floating controller, rebuilds menu labels, and localization supports en/zh-Hant/zh-Hans parsing. | Sources/SignalLanes/main.swift; Sources/SignalLanesCore/SignalLanesLocalization.swift | T001, T006 | Passed | None | No fix needed
F015 | Accessibility prompt | As a user, I can enable precise window switching when Accessibility is not trusted. | Menu title changes based on AXIsProcessTrusted; disabled when already trusted, otherwise prompts via AXIsProcessTrustedWithOptions. | Sources/SignalLanes/main.swift | T002, code inspection | Verified by inspection/build | None | No fix needed | System permission prompt not triggered automatically.
F016 | Status folder and quit | As a user, I can open the override status folder or quit SignalLanes. | Open Status Folder opens FileStatusOverrideStore.directoryURL; Quit terminates NSApp. | Sources/SignalLanes/main.swift; Sources/SignalLanesCore/StatusOverride.swift | T002, code inspection | Verified by inspection/build | None | No fix needed | Quit/open side effects not executed automatically.
F017 | CLI agents | As a CLI user, I can list all supported built-in agent IDs. | agents prints defaultAgentDefinitions IDs and display names. | Sources/signallanesctl/main.swift; Sources/SignalLanesCore/AgentDefinition.swift | T003 | Passed | None | No fix needed
F018 | CLI queue/status | As a CLI user, I can see overall status and Waiting, Running, Stopped task sections. | queue/status constructs AgentDetector, prints overall state, then per-state task sections with source, title, session, reason, and process summaries. | Sources/signallanesctl/main.swift | T004, T005 | Passed | None | No fix needed
F019 | CLI all-known | As a CLI user, I can include idle known tools even when not open. | --all-known passes includeKnownIdleReports and emits idle reports for unmatched definitions. | Sources/signallanesctl/main.swift; Sources/SignalLanesCore/AgentDetector.swift | T001, T004 | Passed | None | No fix needed
F020 | CLI language | As a CLI user, I can choose output language with --lang or SIGNALLANES_LANG. | parseLanguageArguments handles --lang and --lang=value; localization changes headers, state names, reasons, source labels, and usage. | Sources/signallanesctl/main.swift; Sources/SignalLanesCore/SignalLanesLocalization.swift | T001, T006 | Passed | None | No fix needed
F021 | CLI usage/errors | As a CLI user, missing or invalid command shape shows usage or a clear error with a nonzero exit. | usage exits 2; fail writes signallanesctl-prefixed errors and exits 1; state and ttl validation are explicit. | Sources/signallanesctl/main.swift; Sources/SignalLanesCore/SignalLanesLocalization.swift | T007, T001 | Passed | None | No fix needed
F022 | Manual overrides | As a user, I can set, list, and clear manual status overrides with ttl/no-expire and reason text. | FileStatusOverrideStore reads/writes ~/.signal-lanes/status.json atomically, filters expired overrides, and manual reports override automatic state. | Sources/signallanesctl/main.swift; Sources/SignalLanesCore/StatusOverride.swift; Sources/SignalLanesCore/AgentDetector.swift | T001 | Passed | None | No fix needed | Live set/clear was not run to avoid mutating your real override file.
F023 | Unknown manual agents | As a user, I can manually track a tool not in the built-in definitions. | Detector appends overrides whose agentID is not in definitions, using the ID as display name. | Sources/SignalLanesCore/AgentDetector.swift | T001 | Passed | None | No fix needed
F024 | Process snapshots | As a detector user, local processes are parsed accurately from ps output. | PSProcessProvider runs ps -axo pid,ppid,pcpu,stat,command and preserves command lines with spaces. | Sources/SignalLanesCore/PSProcessProvider.swift; Sources/SignalLanesCore/ProcessSnapshot.swift | T001 | Passed | None | No fix needed
F025 | Automatic activity heuristics | As a user, matching agents turn red/yellow/green from process presence, CPU, runnable state, and keywords. | AgentDefinition matching plus assess() handles waiting keywords, working keywords, CPU threshold, runnable state, and processPresence versus cpuOrKeyword modes. | Sources/SignalLanesCore/AgentDefinition.swift; Sources/SignalLanesCore/AgentDetector.swift | T001 | Passed | None | No fix needed
F026 | Built-in agents | As a user, common AI coding tools are recognized without configuration. | Definitions include Codex, Claude Code, Antigravity, Cursor, Windsurf, VS Code, Zed, Xcode, Aider, Gemini CLI, OpenCode, and Goose. | Sources/SignalLanesCore/AgentDefinition.swift | T003 | Passed | None | No fix needed
F027 | Descendant ownership | As a user, child processes launched by an IDE are owned by that IDE and not duplicated under another agent. | captureRoots and isCapturedByOtherDefinition assign descendants to the capturing definition and prevent cross-agent duplicates. | Sources/SignalLanesCore/AgentDetector.swift | T001 | Passed | None | No fix needed
F028 | Project/session extraction | As a user, tasks show project and session context from command-line flags and shell cd commands. | Detector extracts project paths from --cwd, --working-dir, related flags, file URLs, tilde paths, and cd commands; session IDs come from --resume/--session-id. | Sources/SignalLanesCore/AgentDetector.swift | T001 | Fixed + retested | Quoted cd paths with spaces were not extracted. | D002 fixed and retested in T001 | Added quoted cd regression coverage.
F029 | SignalLanes project detection | As a developer dogfooding SignalLanes, an agent working in this repository should still appear in the queue. | Own-tool filtering should exclude the SignalLanes executable/CLI, not any monitored agent whose project path contains SignalLanes. | Sources/SignalLanesCore/AgentDetector.swift | T001, T004 | Fixed + retested | A monitored process with a SignalLanes project path could be filtered out as the app itself. | D001 fixed and retested in T001/T004 | Live queue showed the active Codex SignalLanes session after the fix.
F030 | Task grouping | As a user, sessions are grouped cleanly by IDE/project with highest state and counts. | DetectionResult.taskGroups rolls up same IDE/project tasks to highest state, tracks waiting/running/stopped counts, and preserves raw task list. | Sources/SignalLanesCore/AgentDetector.swift; Sources/SignalLanes/FloatingSignalLanesWindowController.swift | T001, T004 | Passed | None | No fix needed
F031 | Hint/process de-dupe | As a user, IDE session log hints and matching processes do not create duplicate queue rows. | Task hint logic attaches matching processes by session/project and suppresses same-project or ambiguous unprojected process duplicates. | Sources/SignalLanesCore/AgentDetector.swift | T001 | Passed | None | No fix needed
F032 | Codex session hints | As a Codex Desktop user, recent session files produce per-session task hints. | Codex provider scans recent rollout jsonl files, reads session_meta id/cwd, parses tail state, caches parsed sessions, and skips old sessions. | Sources/SignalLanesCore/CodexSessionStatusProvider.swift | T001, T004 | Passed | None | No fix needed
F033 | Codex waiting detection | As a Codex Desktop user, pending approvals turn SignalLanes yellow and completed calls stop waiting. | Tail parsing marks browser calls, escalated commands, apply_patch calls, and browser-like node_repl calls waiting until a matching output/end event; terminal events become idle. | Sources/SignalLanesCore/CodexSessionStatusProvider.swift | T001 | Fixed + retested | Pending apply_patch calls needed explicit approval-prone detection in the current worktree. | D003 fixed and retested in T001 | Existing worktree change was preserved and validated.
F034 | Claude Desktop hints | As a Claude Desktop user, local-agent-mode sessions show active/idle project rows. | Provider scans Claude and Claude-3p local-agent-mode-sessions, skips archived sessions, prefers cliSessionId, selected folders, and recency-based active state. | Sources/SignalLanesCore/ClaudeDesktopStatusProvider.swift | T001 | Passed | None | No fix needed
F035 | Claude Code IDE logs | As an IDE user, Claude Code logs inside Antigravity/VS Code/Cursor/Windsurf produce session hints. | DefaultTaskHintProvider wires AntigravityLogStatusProvider for Antigravity, Code/Insiders/VSCodium, Cursor/Insiders, and Windsurf/Next. | Sources/SignalLanesCore/DefaultTaskHintProvider.swift; Sources/SignalLanesCore/AntigravityLogStatusProvider.swift | T001, T004 | Passed | None | No fix needed
F036 | Antigravity permission fallback | As a user, recent Claude permission requests stay yellow briefly but do not remain yellow forever. | Log provider tracks show_notification/rename_tab permissions, preserves recent pending permission, then falls back to working/idle when stale. | Sources/SignalLanesCore/AntigravityLogStatusProvider.swift | T001 | Passed | None | No fix needed
F037 | Antigravity activity inference | As a user, sessionless log activity still gets useful task/project context where possible. | Provider creates log-derived session IDs, infers project roots from activity file paths, ignores home/config paths, and merges fallback activity into one concrete session. | Sources/SignalLanesCore/AntigravityLogStatusProvider.swift | T001 | Passed | None | No fix needed
F038 | Localization coverage | As a multilingual user, visible labels and common detector reasons are localized. | SignalLanesLocalization covers menu/CLI/floating labels, state labels, source names, dynamic common reasons, queue summaries, and process summaries. | Sources/SignalLanesCore/SignalLanesLocalization.swift | T001, T006 | Passed | None | No fix needed
F039 | Release app bundle | As a release builder, I can produce a local .app with icon and CLI binary. | build-app.sh builds release SignalLanes/signallanesctl, creates .app structure, iconset/icns, and Info.plist with LSUIElement. | Scripts/build-app.sh | T008, T009 | Passed | None | No fix needed
F040 | Installer/package release | As a release builder, I can produce installer, app zip, and CLI zip artifacts. | package-release.sh rebuilds installer and zips .app and CLI; build-installer.sh stages app to /Applications and CLI to /usr/local/bin. | Scripts/build-installer.sh; Scripts/package-release.sh | T010, T011 | Passed | None | No fix needed | Test version used 0.1.0-test.
F041 | Privacy/local data | As a privacy-conscious user, SignalLanes remains local-first. | README states local-only behavior; code reads local ps, local logs/session metadata, and local override JSON without network calls. | README.md; Sources/SignalLanesCore/* | code inspection, T004 | Verified by inspection/build | None | No fix needed | CLI output can display private paths as documented.

## Test Log
ID | Scope | Type | Command/check | Result | Evidence | Retest notes
T001 | Core smoke suite | Automated | swift run SignalLanesCoreSmokeTests | Passed | Covers localization, ps parsing, process heuristics, overrides, grouping, Codex/Claude/Antigravity providers, and new regression fixes. | Ran before and after fixes; final run passed.
T002 | Build all products | Automated | swift build | Passed | Debug build for library, app, CLI, and smoke executable completed. | Final build passed.
T003 | CLI agents | Manual CLI | swift run signallanesctl agents | Passed | Listed 12 built-in agents: codex, claude, antigravity, cursor, windsurf, vscode, zed, xcode, aider, gemini, opencode, goose. | No errors.
T004 | CLI queue | Manual CLI | swift run signallanesctl queue --all-known | Passed | Printed overall Red/working with waiting/running/stopped sections; live output included the active SignalLanes Codex project. | Confirmed D001 in live data.
T005 | CLI status alias | Manual CLI | swift run signallanesctl status --all-known | Passed | Printed the same queue/status structure as queue. | No errors.
T006 | Traditional Chinese CLI | Manual CLI | swift run signallanesctl --lang zh-Hant queue --all-known | Passed | Localized overall label, section headings, source labels, title/session labels, and common reasons. | No errors.
T007 | CLI missing command usage | Manual CLI | swift run signallanesctl | Passed | Exited 2 and printed usage plus examples. | No errors.
T008 | Release app bundle build | Automated script | ./Scripts/build-app.sh | Passed | Built .build/SignalLanes.app and .build/release/signallanesctl. | No errors.
T009 | Bundle metadata/files | Manual shell check | plutil -p Info.plist; ls -l bundle executable/icon/CLI | Passed | Info.plist has LSUIElement true, macOS 14 minimum, icon file, bundle ID; app/CLI executables and icns exist. | No errors.
T010 | Release packaging | Automated script | ./Scripts/package-release.sh 0.1.0-test | Passed | pkgbuild produced installer and script produced app/CLI zip artifacts. | No errors.
T011 | Dist artifacts | Manual shell check | ls -lh dist | Passed | Installer, app zip, and CLI zip exist with nonzero sizes. | No errors.
T012 | App runtime presence | Manual shell check | pgrep -fl SignalLanes | Passed with caveat | A SignalLanes app process from this checkout was already running. | Did not relaunch/kill active app instance.
T013 | Diff hygiene | Automated git check | git diff --check | Passed | No whitespace errors in current diff. | No errors.

## Fixes
Defect | Story | Error found | Files changed | Fix | Coverage added | Retest status
D001 | F029 | Agents working in a project path named SignalLanes could be hidden because isOwnToolProcess filtered any token named signallanes. | Sources/SignalLanesCore/AgentDetector.swift | Changed own-tool filtering to check the executable basename for signallanes/signallanesctl, while keeping explicit signallanesctl and .build app exclusions. | Added testSignalLanesProjectPathDoesNotHideAgentProcess. | Retested by T001 and live queue T004.
D002 | F028 | Quoted shell cd paths with spaces were not extracted because the parser treated the opening quote as a terminator. | Sources/SignalLanesCore/AgentDetector.swift | Added cdArgument parsing for quoted and unquoted cd arguments, preserving paths with spaces and escaped spaces. | Added testQuotedCDProjectPathIsExtracted. | Retested by T001.
D003 | F033 | Codex apply_patch custom tool calls needed to be classified as approval-prone until a patch_apply_end/custom output event arrives. | Sources/SignalLanesCore/CodexSessionStatusProvider.swift | Current worktree includes apply_patch approval-prone detection plus patch_apply_end completion handling. | Added/kept pending and completed apply_patch smoke tests. | Retested by T001.